Project Manual

Project CCS-ITO

| Version: | V1-2 |
| --- | --- |
| Author: | Heinz Hirschi / Thomas Fürst |
| Date: | 27.02.2012 / printed: 27.02.2012 |

Revision

| Version | Author | Changes | Date / Vis |
| --- | --- | --- | --- |
| V1-0 | Th.Fürst/H.Hirschi | Initial document | 14.02.2012 / fut,hih |
| V1-1 | Th.Fürst/H.Hirschi | Div.Anpassungen aus SC-Meeting vom 15.02.2012 - 4.Pilot ergänzt | 22.02.2012 / fut,hih |
| V1-2 | Th.Fürst/H.Hirschi | Pendenzen aus SC-Meeting integriert: - Projektplan angepasst - Projektorganisation | 27.2.2012 / fut,hih |

Index of contents

1	Project Overview	3

1.1	Purpose	3

1.2	Major Tasks	3

1.3	Overall Project Schedule	5

1.4	Project Risks	5

1.5	Basics, Initial Position	6

1.5.1	Origin	6

1.5.2	SCM-Reports	7

1.5.3	Brainstorming with project aspects to be considered	8

2	Project Organisation	9

2.1	Organizational chart	9

2.2	Organisation for Pilot Phase with 4 customers	9

2.3	Points of Contact	10

3	Meeting Cycles	11

3.1	PL meeting	11

3.2	Project team meeting	11

3.3	Steering committee	11

4	Project schedule and resources	12

4.1	Projectplan	12

4.2	Project resources	13

5	Project Controlling	13

5.1	Reports	13

6	Regulations for project documentation	14

# Project Overview

## Purpose

ITO has a general high focus in the EMS sector. The stock situation in the CCS group is not satisfying, it reached 50% of the Material turn over  ITO=2.  CCH & CLK have installed the MTS (Make to Stock) system to increase control over the customer needs, but reduce the own risk level, because of the ability of identifying and charging excess material.

Deviated from the customer MTS control, the inventory should decrease to a acceptable level.

First experiences after installing the system didn’t show an effect on the stock situation.

Main goal of this project is to identify and eliminate bottlenecks and errors within this system and reduce the stock net value minimum 30% within 2 years group-wide.

## Major Tasks

Major Tasks according to the milestones:

| Major Task | Input | Output |
| --- | --- | --- |
| Analysis CCH–CLK | Informations, Interviews, Reports, Observations | Detailed project schedule, bottlenecks, inputs & ideas for further project |
| Comments: | - Which process-steps are ERP-driven and which are manual or by Reports. What were the reasons to set up manually instead of ERP-driven? - Which steps are more/less time consuming than before the MTS setup? - Who/What role is using which information from the reports as described in 1.5.2 SCM-Reports? - Disturbance handling: how is it handled within the process (late delivery, scrap, modifications in the product/within an order)? - Deviations of commitments to customers against suppliers. Will it be analysed and will actions taken to synchronise? |  |
| MTS Pilot with 4 customer | MTS, 4 customer, x products and orders | Evaluation MTS - Operations - Inventory Improvements Potentials |
| Comments: | - Set-up “clean” MTS-System. - Define criteria for successful completion of the pilot. - Monitoring customer orders step by step through all processes (Order Planning, MRP, Purchasing, Material Input, Stock taking, Production, Delivery) and the stock dynamic of RM (Raw material) and FG (Finished Goods) along this timeline. - Which role has a good sight on RM AND FG? - During monitoring, implementation of findings from this and the previous task  just one parameter at the time! - Close cooperation with responsible PM’s. |  |
| Implementation CCH–CLK | MTS incl. improvements and further potentials | Running MTS system, monitoring, inventory reduction |
| Comments: | - Close cooperation with responsible staff in operation and related customers and suppliers. - Appropriate training for the users. - Implementation of all tested findings from the previous step. - These are Quick-wins regarding the duration of this task. - Implementation of reporting and monitoring system. - Stabilization of processes and tasks |  |
| Analysis group-wide - 1st prio: CAH-CAM - 2nd prio: tbd | Informations, Interviews, Reports, Observations | Subsidiaries specific requirements, adjusted project schedule |
| Comments: | - This task is very different comparing to the first Analysis. The employees do not know MTS (exception: Sales) and there is no MTS-process prepared in the system. - CAH-CAM works consequently with the ERP-order proposal, the IDD-Report is just for analysis purposes. - This task is driven together with Process Owners and IT |  |
| Implementation group-wide | Subsidiaries specific requirements, MTS | Running MTS system, monitoring, inventory reduction |
| Comments: | - overall planning and coordination for the implementation - Appropriate training for Key users and users - Implementation step by step |  |

Further Major Tasks, but not part of the CCS-ITO-Project:

- Reworking the past:

To reach the main goal, it is not only necessary to look and control actions in the future, but also in the present.

Therefore, the actual situation and actions like “No movers” analysis, not sold “excess material” will be also on focus within CCS.

The percentage of “old” overstocking in CCH-CLK is yet unknown.

- Group wide report consolidation:

The existing large reports generated from each ERP-System are not easy to consolidate. Initial actions were taken to build a data-warehouse.

The CCS-ITO project – especially in later phases – is depending on good and consolidated reports.

## Overall Project Schedule

More detailed project planning see Chapter 4 Project schedule and resources.

## Project Risks

| Risk | Elimination measures |
| --- | --- |
| Delay in implementation because of under estimated complexity | PL assure priorities |
| MTS concept together with ERP-System(s) too complicated | Pilot |
| MTS in operation not efficient for low stock value | Pilot |
| Missing user acceptance for the MTS-System | Focus on specific user training in advance |
| Group-wide solution not possible due to customer and supplier specific requirements and behaviours | Pilot with 3 customers, early adjustment with involved partners (internally and externally) |
| Group-wide solution not possible due to CCS Subsidiaries specific requirements and behaviours | Analyse phase group-wide |
| Lack of needed project resources | Planning in advance, support by Steering Committee in priority setting |

## Basics, Initial Position

### Origin

What causes led to the development of MTS? Was it a service innovation or caused by internal struggles with systems and/or behaviours? At last a bit of everything.

In an internal discussion, we figured out 3 main reasons:

- Customer demand: Shorter delivery times

With the previous planning system, the safety stock would increase even more. Customer were willing to pay extra to reach shorter delivery times, but customer and producer need a system to monitor the extra service.

- Stock value too high, but still missing parts to start the production

With MTS, the RM (Raw material) is more dedicated to a product/customer and excess should be identified and handled easier.

- Deliveries too late

 Key Performance Indicator DIFOT (Delivery in full on time) too low.

In addition to the previous reason, the planning system in CLK showed more work load than in real.

The „advanced planning system“ within Syteline was therefore switched off and the more manual MTS-process was implemented. The link to the detailled MTS-definitions is listed below.

MTS-definitions:

CCS Point/Global Sourcing/SCM/MTS

All documents relating the CCS ITO project are stored in CCS Point:

CCS ITO Project Folder

The link guides you to the project folder, all prior documents are stored in the subfolder

001_Project_Documentation.

4  Meetings have taken place so far:

30.11.2011:	Kickoff

22.12.2011:	Follow up

12.01.2012:	PL-Meeting

07.02.2012:	PL-Meeting

### SCM-Reports

There are existing detailled reports from all CCS sites, which help in this project:

- Inventory report

Stored in file System CSS, not in CCS Point  very large

w:\Projects_Internal\CCS_other_groupwide_projects\FTC_JetReports\Jet_Report_files\Description_of_the_reports\InventoryValue\

- Purchase Order Report  Order Book

CCH:	CCS Point/Global Sourcing/Procurement/CCH/Procurement_Cockpit

CLK:	CCS Point/Global Sourcing/Procurement/CLK/Procurement_Cockpit

CAH-CAM:	CCS Point/Global Sourcing/Procurement/CAH-CAM/Proc_Cockpit

- IDD (Item Demand Details)

CCH:	CCS Point/Global Sourcing/Procurement/CCH/IDD

CLK: 	CCS Point/Marketing/Delivery_Plan_CLK/IDD_Request_Date

CAH-CAM:	CCS Point/Global Sourcing/Procurement/CCH/IDD

- COS (Customer Order Status Report)

CCH:	?

CLK:	CCS Point/Marketing/Delivery_Plan_CLK

CAH-CAM:	CCS Point/Global Sourcing/Procurement/CCH/COSR

Definition CLK-COS:

CCS Point/Marketing/Delivery_Plan_CLK/ Customer_Order_Status_Report_Documentation

- CMRA (Commodity Management Report Status A)

CCH:	CCS Point/Global Sourcing/Commodity_Mgmt/CMRA/CMRA_CCH

CLK:	CCS Point/Global Sourcing/Commodity_Mgmt/CMRA/CMRA_CLK

CAH-CAM:	File System

To avoid misunderstandings, CCS Group uses the English language terms from Apics:

CCS Point/Global Sourcing/SCM/Apics_Dictionary_2008_SCM_GLOSSAR.pdf

### Brainstorming with project aspects to be considered

# Project Organisation

## Organizational chart

## Organisation for Pilot Phase with 4 customers

Close collaboration with the responsible customer account manager during the pilot phase is recommended. This will give important inputs for operational integration and led to higher acceptance for the MTS-system. The pilot customers and the responsible persons are:

Bartec	Georg Kern

Gilgen	Urs Neuenschwander

CT Concept	Alberto Della Schiava

Maxon – CLK direct business	Peter Schmitt and Andreas Loosli

## Points of Contact

| - Role | Name | Contact Number |
| --- | --- | --- |
| Business Sponsor | CCS Holding |  |
| Steering Committee | Thomas Kaiser TK | +41 32 387 9110 thomas.kaiser@ccsholding.com Skype: thomas.kaiser.ccs |
| Steering Committee | Patrick Oldani OLPA | +41 32 387 9107 patrick.oldani@ccsholding.com Skype: patrick.oldani |
| Steering Committee | Daniel Lippuner LIDA | +41 55 451 7840 daniel.lippuner@ccsholding.com Skype: |
| Project Manager extern | Heinz Hirschi HIH | +41 79 746 4945 heinz.hirschi@affinitas.ch Skype: heinz.hirschi.ch |
| Project Manager intern | Thomas Fürst FUT | +41 55 451 7901 thomas.fuerst@adaxys.com Skype: thomas.fuerst.ccs |
| IT-Manager Navision | Dominique Chatton CHDO | +41 32 387 91.. dominique.chatton@ccsschweiz.com Skype: -- |
| IT-Manager IN:ERP | Roberto Bernasconi BEB | +41 91 640 8456 roberto.bernasconi@adaxys.com Skype: roberto.bernasconi.ccs |
| Logistic Expert | Tobias Heess HET | +41 55 451 7882 tobias.heess@adaxys.com Skype: tobias_heess |
| Process Owner, see Site resp. |  |  |
| Site responsible CLK IT-Manager Syteline | Attila Antal ANAT | Tel.: +94 31 487 1321 Mobile +94 77 368 4450 Attila.Antal@ccalanka.lk Skype: attila.antal_ccs |
| Site responsible CCS /CAH | Norbert Kovacs KONO | +41 32 387 9135 norbert.kovacs@ccsschweiz.com Skype: norbert.kovacs.ccs |
| Site responsible CAM | Annamaria Fejes FEA | +41 91 640 8224 annamaria.fejes@adaxys.com Skype: |
| Pilot CCH-CLK | Georg Kern | +49 7641 933 5980 georg.kern@ccsdeutschland.com Skype:georg_kern_ccs_deutschland |
| Pilot CCH-CLK | Urs Neuenschwander NU | +41 32 387 9138 urs.neuenschwander@ccsschweiz.com Skype: -- |
| Pilot CCH-CLK | Peter Schmitt SP | +41 79 310 49 00 peter.schmitt@ccsholding.com Skype: peter.schmitt.ccs |
| Pilot CCH-CLK | Andreas Loosli LOAN | +41 32 387 9120 andreas.loosli@ccsschweiz.com Skype: andreas.loosli |
| Pilot CCS-CLK | Alberto Della Schiava | +41 32 387 9124 alberto.dellaschiava@ccsschweiz.com Skype: |

Skype users within CCS-Group:

CCS Point/CCS Board Infos & Newsboard/Groupwide_Tools/Skype/Skype_Users_CCS

# Meeting Cycles

## PL meeting

Meeting cycle:	weekly (start-up phase)

Participants:	Heinz Hirschi, Thomas Fürst, (optional: Patrick Oldani)

Responsible for invitation and agenda:  Thomas Fürst

Mandatory: Minutes or task list of the meeting are made for every session

## Project team meeting

Meeting cycle:	tbd after setup phase

Participants:	PL int+ext, project team members

Responsible for invitation and agenda:  Thomas Fürst

Mandatory: Minutes of the meeting are made for every session

## Steering committee

Meeting cycle:	monthly

Participants:	Steering Committee, PL, further on special invitation

Responsible for invitation and agenda:  Thomas Fürst

Mandatory: Minutes of the meeting are made for every session

# Project schedule and resources

## Projectplan

Comments related to project tasks:

## Project resources

The table shows the estimated FTE (Full Time Equivalent) of work load in this period

# Project Controlling

## Reports

Weekly report:

Word template	
Responsible:	Thomas Fürst (Heinz Hirschi)

Cycle:		weekly

Receiver:	Thomas Kaiser, Patrick Oldani

CC:

Resource report:

Excel report (rolling)
Responsible:	Thomas Fürst (Heinz Hirschi)

Cycle:		monthly

Receiver:	Thomas Kaiser, Patrick Oldani

CC:

Costs, expenses and investments report:

Excel report (rolling)

Responsible:	Thomas Fürst (Heinz Hirschi)

Cycle:		monthly

Receiver:	Thomas Kaiser, Patrick Oldani

CC:

# Regulations for project documentation

All Documents are stored in CCS Point.

The following hyperlink guides you to the project folder:

CCS ITO Project Folder

Folder structure in CCS-Point:

01_Project Management

02_Meetings-Minutes

03_general Information

10_Analysis scope CLK - CCH

20_Implementation

30_MTS Pilot

40_Implementation CLK – CCH

50_Analysis group-wide

60_Implementation group-wide

Für die Redaktion stehen die Formatvorlagen Überschrift 1-5 und Fliesstext zur Verfügung.